OfficeShare

Full Project Plan

Flutter  •  Firebase  •  OneSignal

Version 2.0  •  June 2026  •  Mobile Only  •  Internal Use

| Item | Detail |
| --- | --- |
| Project Name | OfficeShare |
| Document Version | v2.0 (Tech Stack Updated) |
| Status | Draft |
| Date | June 2026 |
| Platform | Mobile Only — Android & iOS (Single Flutter Codebase) |
| Frontend | Flutter (Dart) |
| Database | Firebase Firestore + Firebase Storage |
| Authentication | Firebase Authentication (Phone OTP + Google Sign-In) |
| Push Notifications | OneSignal |
| Primary Market | India — UPI Deep Link Payment Flow |
| Selected Features | Bill Splitting • UPI Payment • Personal Tracker • Reminders • WhatsApp Nudge • Approval Workflow • Export (Excel/PDF) |
| Total Sprints | 6 Sprints (12 Weeks — 3 Months) |
| Team Size | 3–4 People (recommended for Flutter + Firebase) |

# 1.  Project Overview

OfficeShare is a Flutter mobile app for Android and iOS that simplifies daily office expense splitting — chai, snacks, lunch — with direct UPI settlement, WhatsApp reminders, an expense approval workflow, and a personal finance tracker. The entire backend is powered by Firebase (Firestore, Auth, Storage, Cloud Functions), and push notifications are delivered via OneSignal.

## 1.1  Why This Stack?

| Decision | Reason |
| --- | --- |
| Flutter (not React Native) | Single codebase for Android + iOS; excellent performance; Material 3 UI; strong pub.dev package ecosystem; Dart is easy to learn |
| Firebase Firestore (not PostgreSQL) | No backend server to manage; real-time listeners out of the box; offline-first data sync; scales automatically; free tier is generous for MVP |
| Firebase Auth (not custom OTP) | Phone OTP and Google Sign-In built-in; no SMS vendor setup; handles token refresh automatically; free up to 10k/month |
| Firebase Storage (not S3) | Integrated with Firebase Auth; security rules for file access; free 5 GB storage; direct upload from Flutter SDK |
| Firebase Cloud Functions (not Express) | Serverless; auto-scale; write business logic in TypeScript; triggered by Firestore events; no server maintenance |
| OneSignal (not FCM direct) | Free tier covers up to 1 million subscribers; dashboard to manage campaigns; easy Flutter SDK (onesignal_flutter); rich notifications with images/actions; no FCM token management needed in code |
| UPI Deep Links (not payment gateway) | Zero cost; opens GPay/PhonePe/Paytm/BHIM natively; no RBI compliance burden; works for 100% of India UPI users |

# 2.  Full Technology Stack

| Layer | Technology / Package | Purpose | pub.dev / Version |
| --- | --- | --- | --- |
| UI Framework | Flutter 3.x (Dart) | Cross-platform mobile app — Android + iOS | flutter.dev |
| State Management | Riverpod 2.x | Reactive state; async providers; testable | flutter_riverpod ^2.5 |
| Navigation | Go Router | Declarative routing; deep links; auth guard | go_router ^13.0 |
| Database | Cloud Firestore | NoSQL real-time database; offline sync | cloud_firestore ^5.0 |
| Authentication | Firebase Auth | Phone OTP + Google Sign-In | firebase_auth ^5.0 |
| File Storage | Firebase Storage | Receipt images; exported files | firebase_storage ^12.0 |
| Serverless Logic | Firebase Cloud Functions (TypeScript) | Split calc; approval triggers; reminder scheduler | firebase-functions v4 |
| Push Notifications | OneSignal | Push to Android + iOS; free tier; rich notifications | onesignal_flutter ^5.0 |
| Local Notifications | flutter_local_notifications | In-app banners when app is open | ^17.0 |
| UPI Payments | url_launcher | Open UPI deep links (gpay://, phonepe://) | url_launcher ^6.3 |
| WhatsApp Nudge | url_launcher + share_plus | wa.me share link; native share sheet fallback | share_plus ^9.0 |
| Excel Export | excel (Dart package) | Generate .xlsx files client-side | excel ^4.0 |
| PDF Export | pdf (dart package) | Generate .pdf files client-side | pdf ^3.10 |
| Charts / Analytics | fl_chart | Pie chart, bar chart, line chart for analytics | fl_chart ^0.68 |
| Image Picker | image_picker | Camera + gallery for receipt upload | image_picker ^1.1 |
| QR Code | qr_flutter + mobile_scanner | Generate + scan invite QR codes | qr_flutter ^4.1 |
| Local Storage | shared_preferences | Cache user preferences, UPI ID, theme | shared_preferences ^2.3 |
| HTTP (optional) | dio | API calls if any external service added later | dio ^5.6 |
| Env Config | flutter_dotenv | Separate dev/staging/prod Firebase configs | flutter_dotenv ^5.1 |

# 3.  Firebase Architecture

## 3.1  Firestore Collections (Database Schema)

Firestore is a document-oriented NoSQL database. Below is the complete collection structure for OfficeShare.

| Collection / Sub-collection | Key Fields | Purpose |
| --- | --- | --- |
| users | uid, name, phone, email, upiId, avatarUrl, oneSignalPlayerId, createdAt | All registered users |
| groups | id, name, companyName, inviteCode, adminUid, approvalRequired, createdAt | Office expense groups |
| groups/{id}/members | uid, role (admin/member/viewer), joinedAt, isActive | Group membership sub-collection |
| expenses | id, groupId, buyerUid, amount, category, description, receiptUrl, splitType, status, approvalStatus, createdAt | All office expenses |
| expenses/{id}/splits | uid, amountOwed, amountPaid, isSettled | Per-person split amounts |
| payments | id, expenseId, payerUid, receiverUid, amount, method, status, proofUrl, createdAt | Payment transactions |
| payments/{id}/disputes | raisedBy, reason, resolvedAt, resolvedBy | Dispute sub-collection |
| approvalRequests | id, expenseId, requestedBy, adminUid, status, comment, decidedAt | Expense approval queue |
| notifications | id, toUid, type, title, body, isRead, relatedId, createdAt | In-app notification feed |
| personalExpenses | id, uid, amount, category, note, date, isRecurring, createdAt | Private personal expenses (user-scoped) |
| personalBudgets | uid, category, monthlyLimit, month (YYYY-MM) | Monthly budget per category |

## 3.2  Firebase Security Rules (Summary)

- users: read/write only by the authenticated user themselves

- groups: read by members; create by any authenticated user; update by admin only

- expenses: read by group members; create by group members; delete by admin or buyer only

- personalExpenses: read/write only by the owning uid — never accessible by other users

- payments: read by payer or receiver; create by payer; confirm/dispute by receiver

- approvalRequests: create by member; update (approve/reject) by group admin only

## 3.3  Firebase Cloud Functions

| Function Name | Trigger | What It Does |
| --- | --- | --- |
| onExpenseCreated | Firestore: onCreate expenses/{id} | Calculate splits, write to expenses/{id}/splits, send OneSignal push to all members, trigger approval request if group.approvalRequired = true |
| onPaymentConfirmed | Firestore: onUpdate payments/{id} (status=confirmed) | Mark related split as settled, send confirmation push to payer via OneSignal |
| onApprovalDecided | Firestore: onUpdate approvalRequests/{id} | If approved: set expense.approvalStatus = approved, notify buyer. If rejected: notify buyer with comment |
| sendDailyReminders | Cloud Scheduler: every day at 9 AM IST | Query all unsettled splits older than 24h, 3d, 7d — send OneSignal push reminder to payers |
| cleanupOldNotifications | Cloud Scheduler: every Sunday midnight | Delete notifications older than 90 days to keep Firestore lean |

# 4.  OneSignal Push Notification Setup

## 4.1  Integration Steps

- Create a OneSignal app in dashboard — configure Android (FCM key) and iOS (APNs certificate)

- Add onesignal_flutter: ^5.0 to pubspec.yaml

- Initialize OneSignal in main.dart on app start

- On user login: call OneSignal.login(userId) to link device to user UID

- Save the OneSignal Player ID to users/{uid}.oneSignalPlayerId in Firestore

- Firebase Cloud Functions use the OneSignal REST API to send targeted pushes

## 4.2  Notification Types

| Notification Type | Trigger | Target | Data Payload |
| --- | --- | --- | --- |
| New Expense Added | Cloud Function: onExpenseCreated | All group members | expenseId, groupId, buyerName, amount |
| Payment Received | Cloud Function: onPaymentConfirmed | Receiver | paymentId, payerName, amount |
| Payment Confirmed | Cloud Function: onPaymentConfirmed | Payer | paymentId, receiverName |
| Expense Approved | Cloud Function: onApprovalDecided | Buyer | expenseId, adminName |
| Expense Rejected | Cloud Function: onApprovalDecided | Buyer | expenseId, adminName, comment |
| Payment Reminder (24h) | Cloud Scheduler daily cron | Unpaid payers | expenseId, owedAmount, receiverName |
| Payment Reminder (3d) | Cloud Scheduler daily cron | Unpaid payers | expenseId, owedAmount, receiverName |
| Monthly Summary | Cloud Scheduler: 1st of month | All users | month, totalSpent, totalOwed |
| Budget Alert (80%) | Cloud Function: onPersonalExpense | Expense owner | category, spent, limit |

## 4.3  OneSignal Flutter Code Pattern

- OneSignal.initialize('YOUR_ONESIGNAL_APP_ID') in main.dart

- OneSignal.login(firebaseUid) after Firebase Auth login

- OneSignal.Notifications.requestPermission(true) on first launch

- Handle foreground notifications with flutter_local_notifications for in-app banners

- Handle notification tap: navigate to relevant screen using Go Router deep link

# 5.  Team Structure & Roles

| Role | Responsibilities | Count |
| --- | --- | --- |
| Product Manager / Owner | Requirements, sprint planning, FRD, stakeholder sign-off, UAT | 1 |
| Flutter Developer (Lead) | Full Flutter app: UI, state (Riverpod), Firebase SDK, OneSignal, UPI, export | 1 |
| Flutter Developer (Junior) | Screens implementation, widget library, testing, bug fixes | 1 (optional) |
| Firebase / Backend Dev | Firestore schema, Security Rules, Cloud Functions (TypeScript), OneSignal REST API, Scheduler | 1 |
| UI/UX Designer | Figma designs, design system (colors, typography, components), user flows | 1 (can be part-time) |

Minimum viable team: 2 people — 1 strong Flutter dev (handles both app + Firebase SDK) + 1 Cloud Functions dev. Designer optional if using Material 3 defaults.

# 6.  Sprint Plan (6 Sprints × 2 Weeks = 12 Weeks)

Each sprint is 2 weeks. Flutter + Firebase enables faster development than a custom backend — no API server to build or deploy separately.

| Sprint | Dates | Goals & Deliverables | Status |
| --- | --- | --- | --- |
| 🏁 PHASE 1 — Foundation (Sprints 1–2) |  |  |  |
| Sprint 1 | Wk 1–2 | Flutter project setup (flavors: dev/prod) • Firebase project config (Android + iOS) • Firebase Auth: Phone OTP + Google Sign-In • User profile screen + UPI ID setup • OneSignal init + permission request • Office Group create / join via invite code • QR code generate + scan | Planned |
| Sprint 2 | Wk 3–4 | Firestore: expenses + splits collections • Add Expense screen (amount, category, members, split type) • Split calculation in Cloud Function (onExpenseCreated) • Expense Dashboard screen (You owe / Owed to you) • Expense History feed with category icons • Receipt upload to Firebase Storage • OneSignal push: New expense added | Planned |
| 🏁 PHASE 2 — Payments & Approval (Sprints 3–4) |  |  |  |
| Sprint 3 | Wk 5–6 | UPI deep link payment screen (url_launcher) • Mark as Paid flow + Firestore payment write • onPaymentConfirmed Cloud Function • Partial payment support • Payment History screen • Settle Up screen (debt simplification algorithm in Cloud Function) • Payment dispute flow | Planned |
| Sprint 4 | Wk 7–8 | Expense Approval Workflow (submit → admin approve/reject) • approvalRequests Firestore collection • onApprovalDecided Cloud Function + OneSignal push • Auto reminders: Cloud Scheduler cron (daily 9 AM IST) for 24h/3d/7d unpaid dues • WhatsApp Nudge (share_plus + wa.me) • In-app Notification Centre screen | Planned |
| 🏁 PHASE 3 — Personal Tracker & Export (Sprints 5–6) |  |  |  |
| Sprint 5 | Wk 9–10 | Personal Expense Tracker: personalExpenses collection + CRUD • Category picker (Food, Travel, Shopping, Health, Rent, EMI, Other) • Budget setup: personalBudgets collection • Budget progress bars + alert at 80% (onPersonalExpense Cloud Function) • Analytics screen: fl_chart pie chart + bar chart + month comparison | Planned |
| Sprint 6 | Wk 11–12 | Export to Excel (excel package, client-side) • Export to PDF (pdf package, client-side) • Save to device + Share via share_plus • Date range picker for export • Full regression testing on Android + iOS physical devices • Performance: Firestore index optimization • Play Store + App Store submission | Planned |
| 🏁 v1.0 Launch — End of Week 12 |  |  |  |

# 7.  Detailed Sprint Breakdown

## Sprint 1 — Foundation & Auth (Week 1–2)

### Flutter App

- flutter create officeshare — set up with flavors: dev, staging, prod

- Add Firebase to Flutter: flutterfire configure for both Android (google-services.json) and iOS (GoogleService-Info.plist)

- Set up go_router: splash, onboarding, OTP, profile-setup, home routes

- Riverpod providers: authProvider, userProvider, groupProvider

- Phone OTP screen with Firebase Auth verifyPhoneNumber flow

- Google Sign-In screen via google_sign_in + Firebase Auth

- Profile setup screen: name, department, UPI ID — write to users/{uid} in Firestore

- OneSignal.initialize() in main.dart; request push permission on onboarding completion

- Create Group screen: name, company name — writes to groups collection

- Invite via QR: qr_flutter to render invite code; mobile_scanner to scan and join

### Firebase (Cloud Functions + Firestore)

- Firestore security rules: users, groups, group_members — auth-scoped

- Cloud Function: onUserCreated — initialize user document in Firestore after Auth registration

### Sprint 1 Done When

- User registers via OTP, sets profile and UPI ID, creates a group, and invites a colleague via QR code — all on a physical Android and iOS device

## Sprint 2 — Bill Splitting Core (Week 3–4)

### Flutter App

- Add Expense screen: TextFormField for amount, DropdownButton for category, CheckboxListTile for member selection, SegmentedButton for split type (Equal / Unequal / Percentage / Shares)

- Dynamic split input: when 'Unequal' selected, show per-member amount fields with live validation (sum must equal total)

- image_picker for receipt: camera or gallery; upload to Firebase Storage at receipts/{expenseId}.jpg

- Expense Dashboard: StreamBuilder on expenses + splits; compute per-person balance client-side using Riverpod

- Expense History: paginated ListView.builder with Firestore query (orderBy createdAt desc, limit 20, startAfterDocument for pagination)

- Category chips with icons (chai, snack, lunch, dinner, travel, other)

### Firebase

- Cloud Function onExpenseCreated: read splitType and members, compute amountOwed per person, batch-write to expenses/{id}/splits

  - Equal: amount / n (remainder assigned to buyer)

  - Unequal: validate sum; write custom amounts

  - Percentage: validate 100%; compute amounts

  - Shares: (userShares / totalShares) * amount

- Firestore composite indexes: groupId + createdAt, groupId + status, uid + createdAt

### Sprint 2 Done When

- Expense added with receipt photo; split correctly calculated; dashboard shows correct balances in real time via Firestore stream

## Sprint 3 — UPI Payments & Settlement (Week 5–6)

### Flutter App

- Payment screen: show receiver name, UPI ID, amount; UPI app selector (GPay, PhonePe, Paytm, BHIM, Any UPI)

- url_launcher deep links: gpay://upi/pay?pa=UPI_ID&pn=NAME&am=AMOUNT&cu=INR

- After returning from UPI app: bottom sheet 'Did you complete the payment?' with Mark as Paid / Cancel

- Mark as Paid: write to payments collection; trigger onPaymentConfirmed Cloud Function

- Partial payment: TextField for amount with max validation

- Payment History: StreamBuilder, filter by sent/received toggle, running balance

- Settle Up screen: display optimised settlement list from Cloud Function result

- Dispute flow: long-press payment → Raise Dispute dialog → write to payments/{id}/disputes

### Firebase

- onPaymentConfirmed Cloud Function: update split.amountPaid, check if isSettled (amountPaid >= amountOwed), send OneSignal push to receiver

- Settle Up callable function: implement minimum cash flow graph algorithm; return list of {payer, receiver, amount} transactions

### Sprint 3 Done When

- Full UPI payment flow tested on physical device with GPay and PhonePe; debt simplification returns correct settlement for a 5-person group

## Sprint 4 — Approvals + Reminders + WhatsApp (Week 7–8)

### Flutter App

- Group Settings screen (admin only): toggle approvalRequired switch → updates groups/{id}

- Pending Approvals tab (admin): StreamBuilder on approvalRequests where status=pending; Approve / Reject with comment dialog

- Expense card shows 'Pending Approval' amber badge until approved

- Notification Centre: StreamBuilder on notifications/{uid} ordered by createdAt; mark as read on tap

- In-app banner: flutter_local_notifications for foreground notifications (OneSignal foreground handler)

- WhatsApp Nudge button on pending payment row: share_plus.Share.shareUri(Uri.parse('https://wa.me/$phone?text=...'))

- Reminder Settings screen: toggle auto-reminders on/off (stored in users/{uid})

### Firebase

- onExpenseCreated: if group.approvalRequired, write approvalRequests document with status=pending; send push to admin via OneSignal

- onApprovalDecided: if approved, update expense.approvalStatus=approved, OneSignal push to buyer; if rejected, push with comment

- Cloud Scheduler (every day 9:00 AM IST): query unsettled splits, group by daysOld (1, 3, 7), send OneSignal push via REST API to payers who haven't settled

### Sprint 4 Done When

- Admin approves expense and buyer receives push; WhatsApp reminder opens on both Android and iOS with correct pre-filled message; cron job runs successfully in Firebase emulator

## Sprint 5 — Personal Expense Tracker (Week 9–10)

### Flutter App

- Personal tab with FAB: Add Personal Expense bottom sheet (amount, category, note, date picker)

- Personal expense list: StreamBuilder on personalExpenses/{uid} ordered by date

- Budget Setup screen: set monthly limit per category; write to personalBudgets collection

- Budget card with LinearProgressIndicator per category; color: green < 60%, amber 60–80%, red > 80%

- Analytics screen:

  - PieChart (fl_chart) — category-wise spending breakdown for selected month

  - BarChart — this month vs last month vs 3-month average

  - Calendar heatmap (custom widget or table_calendar) — daily spend intensity

- Month selector to navigate analytics history

### Firebase

- onPersonalExpenseCreated Cloud Function: aggregate monthly total per category; compare against personalBudgets; if >= 80%, send OneSignal push to user

- Firestore indexes: uid + date, uid + category + date

### Sprint 5 Done When

- User logs 10 personal expenses; budget alert fires when 80% crossed; pie and bar charts render correctly with real data

## Sprint 6 — Export, QA & Launch (Week 11–12)

### Flutter App (Export)

- Export screen: format toggle (Excel / PDF), date range picker (DateRangePickerDialog), member filter

- Excel export: use excel package to build Workbook client-side; columns: Date, Description, Category, Amount, Paid By, Split Members, Status

- PDF export: use pdf package; styled table with header, rows, total row, generated as Uint8List

- Save file: path_provider to get Downloads / Documents directory; then share_plus to send via WhatsApp, email, or Files

- Loading indicator during file generation (large exports)

### QA Checklist

- Test all split types with edge cases: 1 member, max members, sum mismatch

- Test UPI deep links on physical devices: GPay, PhonePe, Paytm, BHIM on Android and iOS

- Test WhatsApp Nudge: correct phone number, correct pre-filled text on both platforms

- Test OneSignal: all 9 notification types received correctly on Android + iOS

- Test offline mode: add expense offline, verify sync on reconnect (Firestore offline persistence)

- Test export: open Excel in Google Sheets, PDF in Google Drive — formatting correct

- Security rules test: attempt to read another user's personalExpenses — must be denied

- Performance: load 100 expenses in group — target < 2 seconds with Firestore indexes

### Launch Prep

- App icons and splash screen: flutter_launcher_icons + flutter_native_splash

- Google Play Store: create listing, upload screenshots (Pixel 7 + tablet), privacy policy

- Apple App Store: App Store Connect setup, TestFlight internal testing, screenshots (iPhone 15)

- Production Firebase project: separate from dev; enable Firestore, Auth, Storage, Functions, App Check

- OneSignal: separate production app; update APP_ID in prod flavor

- Crashlytics: firebase_crashlytics package for crash reporting

- Analytics: firebase_analytics for screen tracking and key events

# 8.  Flutter Project Folder Structure

| Folder / File | Contents |
| --- | --- |
| lib/main.dart | App entry, Firebase init, OneSignal init, Riverpod ProviderScope, Go Router setup |
| lib/core/theme/ | AppTheme (Material 3), color scheme, text styles, component themes |
| lib/core/constants/ | Category enums, UPI app configs, Firestore collection names |
| lib/core/utils/ | Currency formatter (INR), date helpers, UPI deep link builder, WhatsApp link builder |
| lib/features/auth/ | OTP screen, Google sign-in, profile setup, auth_provider (Riverpod) |
| lib/features/groups/ | Group create, invite QR, join screen, group_provider |
| lib/features/expenses/ | Add expense, dashboard, history, expense_provider, split models |
| lib/features/payments/ | UPI payment screen, mark as paid, history, settle up, payment_provider |
| lib/features/approvals/ | Pending approvals list, approve/reject dialog, approval_provider |
| lib/features/reminders/ | Notification centre, reminder settings |
| lib/features/personal/ | Personal expense log, budget setup, analytics screen, personal_provider |
| lib/features/export/ | Export screen, Excel builder, PDF builder |
| lib/features/settings/ | Group settings, profile edit, UPI ID update |
| lib/shared/widgets/ | Reusable widgets: ExpenseCard, PaymentRow, CategoryChip, BudgetBar, AmountDisplay |
| functions/src/ | TypeScript Cloud Functions: onExpenseCreated, onPaymentConfirmed, onApprovalDecided, scheduledReminders |

# 9.  Risks & Mitigations

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| UPI deep link not returning to Flutter app after payment (especially iOS) | High | Medium | Configure Universal Links + Custom URL Scheme; test on 5+ physical devices; use url_launcher canLaunchUrl check before opening |
| Firestore read costs scaling with group size | Medium | Medium | Use Firestore pagination (limit 20); avoid listeners on large collections; aggregate balances in Cloud Function instead of client-side |
| OneSignal push not delivered on iOS (APNs setup) | High | Medium | Configure APNs Auth Key (not certificate) in OneSignal dashboard; test via TestFlight; check entitlements in Xcode |
| Split rounding errors (₹0.01 off) | Medium | High | Use integer arithmetic in paise (₹1 = 100 paise) throughout; assign remainder to buyer in Cloud Function |
| Firestore offline sync conflict on simultaneous expense edits | Medium | Low | Use Firestore transactions for expense creation; soft-lock: only buyer or admin can edit; show last-edited timestamp |
| Export file too large to share on WhatsApp (>16 MB) | Low | Low | Limit export to 3 months max; compress images in PDF; paginate Excel rows |
| Firebase free tier limits exceeded (Spark plan) | Medium | Low | Monitor usage in Firebase console; Firestore free: 50k reads/day, 20k writes/day; upgrade to Blaze (pay-as-you-go) before launch |
| Scope creep delaying launch | High | High | Hard-freeze feature list after Sprint 2; new ideas go to v1.1 backlog in Notion/Linear |

# 10.  Milestones & Success Metrics

| Milestone | Target | Success Criteria |
| --- | --- | --- |
| M1 — Auth + Groups | End of Wk 2 | OTP login, Google login, create group, invite via QR — works on Android + iOS physical device |
| M2 — Split MVP | End of Wk 4 | Add expense (all 4 split types), receipt upload, real-time dashboard balance via Firestore stream |
| M3 — Payments | End of Wk 6 | UPI deep link opens GPay/PhonePe; mark as paid; OneSignal push delivered; settle-up algorithm correct |
| M4 — Approvals + Nudge | End of Wk 8 | Admin approves expense; cron reminder fires in Firebase emulator; WhatsApp nudge opens correctly |
| M5 — Personal Tracker | End of Wk 10 | Personal expense log works; budget alert fires; fl_chart renders pie + bar chart with real data |
| M6 — Launch Ready | End of Wk 12 | All P0 features pass QA on Android + iOS; submitted to Play Store (review) and TestFlight |

## 10.1  Post-Launch KPIs (First 30 Days)

| Metric | Target |
| --- | --- |
| Crash-free Rate (Crashlytics) | > 99.5% sessions |
| OneSignal Delivery Rate | > 95% for all notification types |
| Expenses Logged / Active User / Wk | > 5 expenses per week |
| Payment Settlement Rate | > 70% of dues settled within 7 days |
| DAU / MAU Ratio | > 40% |
| App Store Rating | > 4.2 stars (first 100 reviews) |
| Export Feature Usage | > 20% of users export at least once / month |

# 11.  Post-Launch Roadmap (v1.1 & v2.0)

| Version | Feature | Notes |
| --- | --- | --- |
| v1.1 (Month 4) | Round-Robin Tracker (whose turn to buy) | Firestore queue; Cloud Function auto-rotate; OneSignal push to next buyer |
| v1.1 (Month 4) | Recurring Expense Templates | Save template; local notification to remind buyer; one-tap re-log |
| v1.1 (Month 4) | IOU Peer-to-Peer | Separate from group; simple borrow/lend between 2 users |
| v1.1 (Month 4) | Dark Mode | Flutter ThemeMode toggle; persist in shared_preferences |
| v1.1 (Month 4) | Biometric Lock | local_auth package; optional PIN or fingerprint for app open |
| v2.0 (Month 6) | Web Admin Dashboard | Flutter Web or Next.js; same Firestore data; reports + member management |
| v2.0 (Month 6) | AI Expense Categorization | Claude API: auto-tag category from description text |
| v2.0 (Month 6) | In-App UPI Collect Request | Send UPI collect request via Razorpay/Cashfree; no app switch needed |
| v2.0 (Month 6) | Multi-group Support | User in multiple office groups; separate balances per group |
| v3.0 (Month 9) | Tally / Zoho Books Integration | Sync approved office expenses to accounting software via API |

— End of Document — OfficeShare Project Plan v2.0 — Flutter + Firebase + OneSignal — Confidential —